## Slide 1: Software Process and Quality Management
Case Study
SEWeb and Russoft Technologies
Team Assignment 01

## Slide 2
  Team member list
  Trinh Thai Anh
  Le Ngoc Chau
  Khau Thanh Dao
  Ta Ngoc Thien Phu
  Nguyen Hoang Fa Thu
  Huynh Trong Khang

## Slide 3
  Agenda
  Introduction
  Background
  Relating to subject at hand
  What did people to correctly
  Recommendation
  Reflections

## Slide 4: Introduction
This document is designed for description team Assignment 01 for Software Process and Quality Management
The document focus on description the case study 1: SEWeb and Russoft Technologies
Background: Characters and Events of this Case Study
Relating to subject at hand
What did people do correctly?
What should people have done differently and why?
Reflections

## Slide 5
Background of Seweb Project and Russoft Company

## Slide 6
Background of SEWeb Project and Russoft Company
Characters
Name | Role | Responsibility
Peter Jackson | The new director of the Master of Software Engineering Program at the University of Madison (UV Madison) | Provide requirement (massive redesign and implementation of a new student-faculty-staff Web site) for Gene Fisher Deciding choose team build SEWeb project
Gene Fisher | Project Manager | Manage, monitor and control SEWeb project
Alex Rau | Webmaster Technical Lead | Coordinate, test, and monitor this offshoring development project under Fisher’s supervision
Jane Weber | Program Administrator | Get high level requirement
Al Molsters | System Administrator | Get high level requirement
Project Team

## Slide 7
Background of SEWeb Project and Russoft Company
Characters
Name | Role | Responsibility
Russ Laughlin | Russoft’s CEO | Manage Russoft’s team
Dennis Bramer | Account Manager Russoft’s U.S. managing director | Count time and collect/report working hour Build a basic level plan
Mikhail Pisarev | Russoft’s Technical Manager Russoft’s Technical Director | The project leads, to discuss the speciﬁcs on GUI design, ongoing issues that needed to be resolved, and the planning
Sergey Nizamov | Russoft’s Team Lead | The project lead on the Russian side
Russoft Project Organization

## Slide 8
Background of SEWeb Project and Russoft Company
Characters
Name | Role
Yuri Kashnovsky | Had just founded LearnIT, Inc.
Emillio Arroyo-Lopez | the Argentinean-born director of the department’s distance education program
Mukhit Ashgirov | a student from Kazakhstan
Natalya Girienko | a student from Russia
Oksana Milov | a student from the Ukraine
Peter Kower | The partner with Russ Laughlin in a few business initiatives
John Foote | faculty member
Levin | professor of computer science
Another Relative Characters

## Slide 9
Characters
Events
Background of SEWeb Project and Russoft Company
K 1 6 T 1
BigFive
®
In Fall 2002
In late summer 2002
August 2003
September 2003
In late October 2003
November 2003
E1: Peter Johnson, the new director of the Master of Software Engineering Program at the University of Madison (UV Madison), he gave the project to Fisher.
E2: The budget was small ($5000) so Fisher decided to look for an offshore development team instead of one in the United States.
E3: Fisher decided to send out requests for proposals to four other companies besides Russoft are LogicArt, Wisto Technologies, Grapple Effects and DesignIT solutions.
E4: Fisher went to Russoft Technologies Corporation and choose it for SEWeb project, a decision that conﬁrmed his initial “gut feeling.”

## Slide 10
Characters
Events
K 1 6 T 1
BigFive
®
In Fall 2002
In late summer 2002
August 2003
September 2003
In late October 2003
November 2003
E5: Fisher and Arroyo-Lopez also met with the two co-chairs of the Information Technology and Telecommunications Committee of the American Chamber of Commerce in Moscow..
E6: To get the list of requirements, Fisher and Rau interacted for more than three months with Johnson and Arroyo-Lopez, the other full-time faculty, the department support personnel and program managers, current students, some of the program alumni, program mentors, and so on
Toward the end of their visit
Three months later of end of their visit

## Slide 11
Characters
Events
K 1 6 T 1
BigFive
®
In Fall 2002
In late summer 2002
August 2003
September 2003
In late October 2003
November 2003
E7: Prof. Peter Johnson was taking over the position of program director from Prof. Ed Schubert. Johnson, a pioneer in the ﬁeld of software architecture, decided to increase the Web presence of the professional programs in software engineering through a rollout of a new Web interface.
E8: Fisher instructed Rau to search for samples from known Websites with a similar look and feel to get some of the faculty comfortable with the particular design they had chosen.
When Fisher shared the designs with UV Madison team

## Slide 12
Characters
Events
K 1 6 T 1
BigFive
®
In Fall 2002
In late summer 2002
August 2003
September 2003
In late October 2003
November 2003
E9: Fisher was in Moscow for a teaching seminar. He used the business excursion to also meet with Russoft and discuss how things were going. He approached Sergey Nizamov and Russ Laughlin from Russoft to arrange a meeting to see their office firsthand and to discuss project specifics. He also spoke to Bramer in the US to learn how the project was going from his perspective and to obtain a detailed account of the hours spent, though the later information was not provided.

## Slide 13
Characters
Events
K 1 6 T 1
BigFive
®
In Fall 2002
In late summer 2002
August 2003
September 2003
In late October 2003
November 2003
E10: Fisher and Russ Laughlin brought in Sergey Nizamov and Mikhail Pisarev to discuss the specifics on GUI design, ongoing issues that needed to be resolved, and the planning that lie ahead on them.
E11: Fisher updated both Bramer and his own department about his visit in Moscow. He asked Bramer to provide him with a formal count of the hours spent on the project thus far.
June 2003
E12: The project plan was laid out
The new semester had already started
E13: Fisher was uncertain whether the ongoing communication issues that he and Rau were observing were caused by an issue they themselves had created, a cultural or language barrier, or a misinterpretation of the requirements communicated by Bramer to the Russians when the project originally started.

## Slide 14
Characters
Events
K 1 6 T 1
BigFive
®
In Fall 2002
In late summer 2002
August 2003
September 2003
In late October 2003
November 2003
E14: Fisher was notiﬁed that Bramer was leaving the project and Russoft.

## Slide 15
Characters
Events
K 1 6 T 1
BigFive
®
In Fall 2002
In late summer 2002
August 2003
September 2003
In late October 2003
November 2003
E15: Fisher traveled to Russia for yet another teaching engagement, he finally met with Russ Laughlin and his new ly appointed U.S. project manager, Mark Urlanski, at a local restaurant in Moscow.
Back in his ofﬁce the following week
E16: While the requirement was to use an open source MySQL implementation, Sergey had decided to use Microsoft SQL Server, a different and costly database. The change might not have been a problem, but the stakeholders had not discussed it beforehand
E17: Fisher had negotiated our hourly cost down to the bare minimum for a fixed-cost contract.

## Slide 16: Relating to Subject at hand
Software Project Management (SPM)
Requirement Engineering (RE)
Group Dynamics and Communication
Software Measurement and Analysis
Software Architecture & Design (SAD)

## Slide 17: Correctly & Incorrectly
Recommendation
Nguyen Hoang Fa Thu

## Slide 18: What did people do correctly and Recommendation
1. Redesign and implementation of a new student-faculty-staff Web site to expand the national and international reach of the program. Johnson wants to simplify and coordinate the information of software engineering program because the current Web site is outdated and doesn’t look good  Correct
2. Johnson gave the project to Fisher with the small budget, minimal approval and oversight required.  Something correct and The other incorrect
If Fisher wanted to do well, before start this project he must learn more about the old system to get experience and understand it.
3. Fisher conducted a search to understand both the technical capabilities that the potential service provider would need and the costs associated with implementing the system. Fisher recalled what had led to the decision to look for an offshore development team instead of one in the United States.  Something correct and The other incorrect
Before choose a resource to outsource a project, we must collect information about them, such as: traditional, how do they do, level.

## Slide 19: What did people do correctly and Recommendation
4. Fisher to go with Russoft Technologies Corporation, a decision that confirmed his initial “guts feeling.”  Incorrect
When consider choosing resource for project, we need pay a lot of attention to understand our colleagues. We need to analyze trade off to make the best decision.
5. Fisher received the assistance of Alex Rau to fathering Initial Requirements. Rau had just been hired for the Webmaster position, to help with requirements. Rau was tasked to help coordinate, test, and monitor this offshoring development project under Fisher’s supervision..  Incorrect
When consider choosing resource for project, we need pay a lot of attention to understand our colleagues. We need to analyze trade off to make the best decision. When applied into Web position.
6. Used a list of questions given to Fisher by Russoft as one of the tools to gather requirements.This was a standard way of doing business for them, and they used our input to make the final proposal..  Incorrect
Must combine more skill, tool to gathering requirement, From that, we must analyses to go finally requirement what is used like standard.

## Slide 20: What did people do correctly and Recommendation
7. Divided the project into two phases. It was agreed that currently only Phase 1 would be contracted, estimated, and budgeted. When time and budget permitted, a business arrangement would be further negotiated to the satisfaction of both the client and the software developer. Incorrect
Before start a project, you must estimate, plan, and make schedule for project to used and control resource effectiveness.
8. Didn’t want to spend too much time collecting requirements. There wasn’t enough time in the plan anyway for it. Get into design fast so that using most of our hours for coding rather than talking...  Incorrect
You can negotiate with customer to be confirmed resource to do..
9. Fisher instructed Rau to search for samples from known Websites with a similar look and feel to get some of the faculty comfortable with the particular design they had chosen.  Incorrect
The first view: Using Websites reference as their design to speed things up and clear any misunderstandings: it’s wrong.
The second view: If they use that for reference to get ideal and reduce time: it is true. (SRE: prototype).

## Slide 21: What did people do correctly and Recommendation
10. Sergey had decided to use Microsoft SQL Server while the requirement was to use an open source MySQL implementation. Incorrect
You must develop a management plan to control project in resource which you have. Specially, you must have Change management plan which is response when have change
.11. Didn’t want to spend too much time collecting requirements. There wasn’t enough time in the plan anyway for it. Get into design fast so that using most of our hours for coding rather than talking...  Incorrect
You can negotiate with customer to be confirmed resource to do..
12. Communication by mail in project..  Incorrect
Change how to communicate with other to not lost information. Before change something, you must notify and wait for to be confirm form customer

## Slide 22: Yes or No
Quality
Huynh Trong Khang

## Slide 23
Quality Characteristic
  Process
  People
  Technologies
  Schedule, budget

## Slide 24: In this project, Quality was a dominant characteristic but project team didn’t focus on it!

## Slide 25
Quote: Fisher asked for bids from LogicArt, a New York-based company with Russian operations; Wisto Technologies, a large India-based company headquartered in Oakbrook, Illinois; Grapple Effects, a Cleveland-based company; and DesignIT solutions located in San Jose, California. Even though formal criteria for deciding among them were not explicitly defined, a simple analysis including cost, references or reputation, location, and experience convinced Fisher to go with Russoft Technologies Corporation, a decision that confirmed his initial “gut feeling.”
Quality Characteristic in the project
Process
Conclusion: The project didn’t have a software development process and specific plans.The project needs to choose a development process (traditional methodology) because requirements little change and team development of project from somewhere in the world.

## Slide 26
Quote:
Bramer didn’t want to spend too much time collecting requirements and the project do not focus it.
Fisher want to reduce the time taken for the requirements and design, and focus for coding
Quality Characteristic in the project
Process
Conclusion: Fisher didn’t have attend to manage risk
Quote:
While the requirement was to use an open source MySQL implementation, Sergey had decided to use Microsoft SQL Server, a different and costly database. The change might not have been a problem, but the stakeholders had not discussed it beforehand.
Conclusion: The project didn’t have change process management to Sergey know how to do when there is a change

## Slide 27
Quote:
Fisher assigned Alex Rau to keep him in the loop through his e-mail communication with Sergey Nizamov
Quality Characteristic in the project
Process
Conclusion: The project didn’t have implement technical review process and inspection to ensure quality

## Slide 28
Quality Characteristic in the project
Process
People
Quote:
Fisher assigned Alex Rau to keep him in the loop through his e-mail communication with Sergey Nizamov
Conclusion: Requirement specification didn’t have approval and base line with stakeholders
Quote:
Fisher received the assistance of Alex Rau, a new person with very little experience who had just been hired for the Webmaster position, to help with requirements. Rau was tasked to help coordinate, test, and monitor this offshoring development project under Fisher’s supervision
Conclusion: Fisher didn’t have train for new people and makes decision follow his emotion.

## Slide 29
Quality Characteristic in the project
Process
People
Technology
N/A

## Slide 30
Quality Characteristic in the project
Process
People
Technology
Quote:
Sergey really didn’t have an exact answer for this. He said he thought they had spent about 30 to 40 hours so far. Fisher was very pleased with his answer.
Conclusion: Project didn’t have a schedule details and estimation the number of hours before do.
Quote:
Fisher was always concerned that they had not budgeted for travel in this project to meet their vendors
Conclusion: Fisher didn’t have estimate all budgets for activities relating the project. Fisher needs to make a list of project cost (development, resources, travel, salary,…) and negotiate with customer to get an appropriate budget.
Sche/Bud

## Slide 31
K16T1
BigFive
Thank you!